## Summary
Three Point Estimation Sheet
Client Name |  |  |  |  | CAMMS
Project Name |  |  |  |  | CAMMS Risk - Upload
Type of Implementation and Tech Stack |  |  |  |  | Web
Input Information Reference
Nature of the Deveopment / Requirement |  |  |  |  | Action Approval, Settings , Validations and Permissions
Estimation condition % against the available information |  |  |  |  | 70%
No | Assumptions |  |  |  |  | No | Risks
1 | 0.5 Snr Developer for FE, 0.5 Snr Developer for BE,1 QA(On Site) |  |  |  |  | 1 | System up and running
2 | Frontend _ReactJS |  |  |  |  | 2 | System not executing for Happy Path
3 | Backend_NodeJS |  |  |  |  | 3 | Connection issues
4 | Database_MySQL |  |  |  |  | 4
5 | Cloud Deployment_DigitalOcean linux droplet |  |  |  |  | 7
6 | User roles - Admin, KCULLUser, WeightUser | [5 empty] | Total
7 | Only one user will be able to have the file open at any time. Other user will not be able to use the file untile the currenct user close the file. The file will be deleted from the source location and a record will be added to the database - Initial idea was to use a SFTP file browser but this might not be possibel to directly connect with a SFTP server from a web app. We may need to consider other options. Involves R&D Google drive picker may be a good alternative if SFTP is not possible - https://www.youtube.com/watch?v=kjs3bZxchLY
8 | Get the weight results from as a input from the weighing scale device - Involves R&D
9 | data will be saved to database as well
10 | export all or filtered data with updated values to excel
11 | export all or filtered data with updated values to excel
Total Risk Days
Update by CEO/CTO
# | Task |  | Best Case[In Days] |  | Worst Case[In Days] | Most Likely Case[In Days] |  | Finalised Effort[Days] | Rate | Cost |  | Required Days with Allocation | Week
1 | BA |  | 5 |  | 7 | 6 |  | 5 |  | 0 | 0 | 5 | 1
2 | UI/UX |  | 5 |  | 7 | 6 |  | 5 |  | 0 | 0 | 5 | 1
3 | Development |  | 6.5 |  | 14 | 9 |  | 100 |  | 0 | 40 | 100 | 20
4 | QA |  | 2 |  | 5 | 3 |  | 20 |  | 0 | 30 | 40 | 8
5 | Tech Lead |  | 3 |  | 5 | 4 |  | 8 |  | 0 | 0
6 | Project Manager |  | 3 |  | 4 | 3 |  | 5 |  | 0 | 0
7 | [7 empty] | 0 |  | 0
8 | [7 empty] | 0 |  | 0
9 | [7 empty] | 0 |  | 0
10 | [7 empty] | 0 |  | 0
| Totals |  | 24.5 |  | 42 | 31 |  | 143 |  | 0
Responsibility |  | Designation |  | Name
Form filled By |  | PM

## Details
Task | Subtask | Assumptions / Technical comments | Front End Estimation in Man Days |  |  | Back End Estimation in Man Days |  |  | Integration Estimation in Man Days
|  |  | Worst case | Most likely case | Best Case | Worst case | Most likely case | Best Case | Worst case | Most likely case | Best Case
Policy, Compliance, Audit, Audit recommendation & Audit findings | Policy |  | 0.5 | 0.25 | 0.125 | 2 | 1.5 | 1.25
| Compliance |  | 0.5 | 0.25 | 0.125 | 1.5 | 1 | 0.75
| Audit |  | 0.5 | 0.25 | 0.125 | 1.5 | 1 | 0.75
| Audit recommendation |  | 0.5 | 0.25 | 0.125 | 1.5 | 1 | 0.75
| Audit findings |  | 0.5 | 0.25 | 0.125 | 1.5 | 1 | 0.75
Remove the Bow tie option from the left hand navigation as communicated earlier |  |  | 0.5 | 0.25 | 0.125
Zoom in functionality - vertically |  | Need to do R&D first | 3 | 2 | 1.5
Linked Risk widget(no details in updated xd) |  | (no details in updated xd)
Risk appetite on Risk widget (no details in updated xd) |  | (no details in updated xd)
|  |  | 6 | 3.5 | 2.25 | 8 | 5.5 | 4.25 | 0 | 0 | 0
|  |  | Worst case | Most likely case | Best Case
Tech stack |  |  | 14 | 9 | 6.5
Frontend
Backend
Database
Cloud Deployment

## High-Level Schedule
Task/Epic | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8